## 1. READ THIS FIRST!
READ THIS FIRST! This DOCUMENTARY BUDGET, SCHEDULE & FINANCE PLAN TEMPLATE was created by Robert Bahar alongside the article "A Fresh 2025 Look at Documentary Budgeting and Scheduling (with new templates!)" published by the INTERNATIONAL DOCUMENTARY ASSOCIATION. (Both the article and template are © 2024 Robert Bahar.) HOW TO USE THIS TEMPLATE 1. ARTICLE: Before using this template, please first read the article at https://www.documentary.org/online-feature/2025-introduction-documentary-budgeting-and-scheduling for a deep exploration of documentary budgeting and scheduling. 2. SCHEDULE: The SCHEDULE tab is new! Before you can make a budget you will need to create a schedule to see how much shooting, editing, travel, etc. is planned, and how long each crew member or resource will be needed. Without this information, you cannot make an accurate budget. (And, whenever you revise your schedule, you will also need to revise your budget.) 3. BUDGET GLOBALS: Once you have a schedule, and before you start budgeting, you have the option to create "Globals" on the BUDGET GLOBALS tab. Globals are numbers that will be needed frequently in your budget - like the number of shooting days or the number of edit weeks. Instead of entering these numbers on dozens of lines in the budget, you can enter them once on the Budget Globals tab and then use them "globally" throughout your budget. This makes adjustments easier and can save work and help prevent mistakes. For detailed instructions, see the Budget Globals tab. (If you choose not to use Globals, you will simply need to delete the name of each Global when it appears in a formula on the Budget Detail tab, and replace it with an actual number.) 4. BUDGET DETAIL: The bulk of your time will be spent slowly working through the BUDGET DETAIL tab, adapting each line item to your film's needs. Because each project is unique, you may find that this template is a great match for your project and needs few adaptations, or you may find that you need to adapt it significantly, for example, to add new line items for needs not covered by the template. Don't delete the lines that don’t match your needs till the very end though – keeping everything visible as long as possible will really help as you are brainstorming. Once you are finished though, you may choose to delete empty accounts (lines with zero being spent) to simplify your final budget. (That said, never delete a line that has zero cost but that does factor into your project. For example, if your sound person is budgeted at zero because you, as director, will be handling sound, leave the line for sound recordist where it is and just add a note saying “Director will handle sound”. That way, no one thinks you forgot to think about sound.) Also, at the top of the Budget Detail tab, there are some basic project assumptions to fill in, such as the director and producer's names, shooting format, etc. There is also a mini-schedule that should calculate based on the Globals, if you are using them. 5. BUDGET TOPSHEET: The BUDGET TOPSHEET is a summary of your budget and should calculate automatically from the Budget Detail. It should also automatically copy the film title, budget date, and budget assumptions from the Budget Detail. Please double check that everything has come through properly though. 6. FINANCE PLAN: In another new addition, there is now a FINANCE PLAN tab, which you will likely need to submit along with your budget. 7. CURRENCY: This template is only designed to track a single currency - please adjust/use the budget with the currency that fits your needs. For projects shooting in multiple countries, or for co-productions that span multiple currencies, you may need to customize the template considerably. 8. DOUBLE-CHECKING: Always double check your work! For example: do the subtotals on the Budget Detail tab add up to the total at the bottom? Do the Budget Detail tab and the Budget Topsheet match? Remember, because this template is provided in an open format, it is possible that you will accidentally delete or change a formula, especially if you add/delete lines. Always double check everything carefully. 9. MAKING A FINAL PDF: Most budgets are submitted in PDF format. To create a final PDF, you will first need to export/"print as PDF" the Budget Topsheet and Budget Detail separately and then combine them into a single PDF using any PDF software. When you export, be careful that the margins are clean and, if necessary, select the correct print area on the spreadsheet to display the budget correctly. You may choose to include the Finance Plan in the same PDF as the budget, or to present it as a separate document. The Schedule would generally also be a separate document, but it's worth noting that many funders will just ask for a few paragraphs or a brief production timeline, rather than the full detailed schedule. 10. HELP WITH GOOGLE SHEETS OR MICROSOFT EXCEL: This template was developed and tested in Google Sheets and should work in both Google Sheets (free) and Microsoft Excel. If you need help learning either one, there are numerous helpful tutorials on YouTube and other sites. 11. A FINAL NOTE: Please be patient and remember that even an experienced documentary producer may need two weeks to properly schedule and budget a feature length documentary film. There is no substitute for the hours of research, e-mails and phone calls required to properly plan a film production, or for the advice of experienced local producers, directors, crew and vendors who have made similar films or worked in similar places, and who can provide recent, first hand experience. ACCESSIBILITY Another exciting addition to this template is the inclusion of numerous line items relating to accessibility for D/deaf/hard-of-hearing, blind/low vision, disabled, and neurodivergent film crew, film participants and audiences. These line items generally have budget account codes that end with “80”. (For example, 2080, 4080, 4180, etc.) Note that some of these line items are filled in with actual costs, such as the closed captions and audio description services that will help make your film accessible to audiences and your team during production and post (i.e. captioned scenes or rough cuts). Other line items, however, are quite specific to the unique access requirements of your crew and participants, and list several options for you to budget based on individual requirements. As described below in “STORY CONCEPT & BUDGET ASSUMPTIONS”, for the purpose of this template as an example, we have assumed that the Production Manager is a wheelchair user, and have budgeted appropriately for her accessibility needs. For more details, please see "Part VI. Accessibility" in the budgeting article. Special thanks to FWD-Doc for having consulted on the accessibility-related aspects of this budget template, and without whose guidance this wouldn't have been possible, and special thanks for the generous support of Concordia Studios and The Concordia Fellowship for supporting this consultation. Special thanks to DPAN for feedback regarding accessibility, captions, audio descriptions and ASL interpretation. And special thanks to IDA for helping to inspire and manage this consultation process. STORY CONCEPT & BUDGET ASSUMPTIONS In order to make any budget, including this template, we need to know what story that we are telling, how that story will be told, and some other basic project assumptions. For this template, we have assumed that we are telling the story of a local community struggle somewhere in New York State, filmed largely in cinema vérité, shooting approximately 1 day per week for 12 months, with 10 sit-down interviews for context and background, and approximately 3 minutes of archival footage. (Please note that this is just an example. There are many other wonderful styles of documentary films including all-archival, personal essay, animation, doc-fiction hybrid, experimental, poetic, etc. The documentary form is infinite and this is merely one of many approaches that could have been chosen for this template!) Regarding the team, we assume that the film is being led by two people: a Director/Writer/DOP/Co-Producer who will shoot the cinema vérité days herself, and a Producer/Writer/Sound Recordist who will handle sound on the cinema vérité days himself. The interviews will require a bigger crew including a Director of Photography, Camera Assistant, Sound Recordist, Gaffer, Makeup and Data Wrangler, and the Director and Producer will not handle any of those roles on interview days. (For vérité/visuals days, the Data Wrangler will come every 3 days.) As mentioned under “ACCESSIBILITY” above, we have also assumed that the Production Manager is a wheelchair user, and have budgeted appropriately for her accessibility needs. Finally, we have assumed that production & editing will take place in New York, that the Director and Producer are local to the story and only need to travel for 2 interviews, that employees are subject to New York State payroll costs, and that the project is subject to US law. DISCLAIMER This template is designed as a teaching tool and the numbers in it are based on specific assumptions regarding story, schedule, team, location, etc., as described above. It is offered as a guide but should not be considered exhaustive. Each project has its own unique needs and you may need to make substantial changes to adapt this template to your project and process, or even to rewrite it completely. It is also important to acknowledge that budget formats, strategies and costs vary widely depending on professional experience levels, funder requirements, documentary traditions, film cultures, funding access, and geographical backgrounds. Please note that, while it has been made with great care, this template is offered "AS-IS" and is not guaranteed to be free of errors or omissions. Use it at your own risk, double check everything, and please consult with an experienced documentary producer, line producer or production manager for professional advice. SHARING AND DISTRIBUTION OF THIS ARTICLE AND TEMPLATE The article "A Fresh 2025 Look at Documentary Budgeting and Scheduling (with new templates!)" and this template may be linked to freely by documentary film organizations, film funders, film schools, and filmmakers on the condition that it is not modified, it is not sold, and that it is properly credited. Please ONLY share the template via the original article link, so that it will always link to the most updated version. ACKNOWLEDGEMENTS Special thanks to Producer Lisa Remington for reviewing multiple drafts and providing ample feedback, and for years of truly excellent advice on earlier budget templates as well. Special thanks to Producer Itziar Garcia Zubiri for much guidance and support. Special thanks to FWD-Doc for having consulted on the accessibility-related aspects of this budget template, and for the generous support of Concordia Studios and Concordia Fellowships for supporting the consultation with FWD-Doc. Special thanks to DPAN-TV for feedback regarding accessibility and captions, audio descriptions, ASL interpretation, etc. Finally, special thanks to editor Abby Sun and IDA for inviting me to update this article/template, for helping to inspire and manage the accessibility consultation, and for much input along the way. THANK YOU AND HAPPY BUDGETING! © 2024 Robert Bahar

## 2. Schedule
0 | UNTITLED EXCELLENT DOCUMENTARY FILM |  |  |  | Schedule Date: 3/1/2024 | [9 empty] | Prod/Dir |  | Production staff |  |  |  | Research | Archive |  | Editorial
MONTH | WEEK | MONDAY DATE | FUNDRAISING | STORY RESEARCH | ARCHIVAL |  | SHOOT |  | EDIT |  | MUSIC | POST |  | DISTRIBUTION + IMPACT | Director/Writer/DOP | Producer/Writer/Sound | Production Manager | Prod/Acctg Coord | Post Super | Office PA | Story Researcher | Archival Researcher 1 | Archival Researcher 2 | Editor | AE | Add'l AE
| 1 | 2024-04-29 | Continue | Begin/continue | [10 empty] | 1 | 1
Month 1 | 2 | 2024-05-06 | fundraising | story + | [10 empty] | 2 | 2
2024-05-01 | 3 | 2024-05-13 |  | investigative + | [10 empty] | 3 | 3
| 4 | 2024-05-20 |  | legal research | [10 empty] | 4 | 4
| 5 | 2024-05-27 | [12 empty] | 5 | 5
| 6 | 2024-06-03 | [12 empty] | 6 | 6
Month 2 | 7 | 2024-06-10 | [12 empty] | 7 | 7
2024-06-03 | 8 | 2024-06-17 | [12 empty] | 8 | 8 |  | Orange
| 9 | 2024-06-24 | [12 empty] | 9 | 9 |  | means part-time
| 10 | 2024-07-01 | [12 empty] | 10 | 10 | 1 | << PM 1/2 time |  | 1
Month 3 | 11 | 2024-07-08 | [12 empty] | 11 | 11 | 2 |  |  | 2
2024-07-01 | 12 | 2024-07-15 | [12 empty] | 12 | 12 | 3 |  |  | 3
| 13 | 2024-07-22 | [12 empty] | 13 | 13 | 4 |  |  | 4
| 14 | 2024-07-29 | [12 empty] | 14 | 14 | 5 |  |  | 5
| 15 | 2024-08-05 |  |  |  |  | the letter "i" below = interview shoot day | [7 empty] | 15 | 15 | 6 |  |  | 6
Month 4 | 16 | 2024-08-12 |  |  |  |  | the letter "v" below = visuals/vérité shoot day | [7 empty] | 16 | 16 | 7 |  |  | 7
2024-08-05 | 17 | 2024-08-19 | [12 empty] | 17 | 17 | 8 |  |  | 8
| 18 | 2024-08-26 |  |  |  |  | 1v Prep/Cam test | [7 empty] | 18 | 18 | 9 |  |  | 9
| 19 | 2024-09-02 |  |  |  |  | 1v | [7 empty] | 19 | 19 | 10 |  |  | 10
Month 5 | 20 | 2024-09-09 |  |  |  |  | 1v | [7 empty] | 20 | 20 | 11 |  |  | 11
2024-09-02 | 21 | 2024-09-16 |  |  |  |  | 1v | [7 empty] | 21 | 21 | 12 |  |  | 12
| 22 | 2024-09-23 |  |  |  |  | 1v | [7 empty] | 22 | 22 | 13 |  |  | 13
| 23 | 2024-09-30 |  |  |  |  | 1v | [7 empty] | 23 | 23 | 14 |  |  | 14
| 24 | 2024-10-07 |  |  |  |  | 1v | [7 empty] | 24 | 24 | 15 |  |  | 15
Month 6 | 25 | 2024-10-14 |  |  |  |  | 1v | [7 empty] | 25 | 25 | 16 |  |  | 16
2024-10-07 | 26 | 2024-10-21 |  |  |  |  | 1v | [7 empty] | 26 | 26 | 17 |  |  | 17
| 27 | 2024-10-28 |  |  |  |  | 1v | [7 empty] | 27 | 27 | 18 |  |  | 18
| 28 | 2024-11-04 |  |  | Start archive |  | 1v | [7 empty] | 28 | 28 | 19 |  |  | 19 |  | 1 | << Archivist 2 dys/week
Month 7 | 29 | 2024-11-11 |  |  | search |  | 1v | [7 empty] | 29 | 29 | 20 |  |  | 20 |  | 2
2024-11-04 | 30 | 2024-11-18 |  |  |  |  | 1v | [7 empty] | 30 | 30 | 21 |  |  | 21
| 31 | 2024-11-25 |  |  |  |  | 1v | [7 empty] | 31 | 31 | 22 |  |  | 22
| 32 | 2024-12-02 |  |  |  |  | 1v | [7 empty] | 32 | 32 | 23 |  |  | 23
Month 8 | 33 | 2024-12-09 |  |  |  |  | 1v |  | AE starts logging archive | [5 empty] | 33 | 33 | 24 |  |  | 24 |  |  |  | 0.4 | 1
2024-12-02 | 34 | 2024-12-16 |  |  |  |  | 1v |  | & visuals/vérité | [5 empty] | 34 | 34 | 25 |  |  | 25 |  |  |  |  | 2
| 35 | 2024-12-23 |  |  |  |  | 1v |  | per Editor's guidelines | [5 empty] | 35 | 35 | 26 |  |  | 26 |  |  |  |  | 3
| 36 | 2024-12-30 |  |  | Archive needs? |  | 1v | [7 empty] | 36 | 36 | 27 |  |  | 27 |  | 3 |  |  | 4
| 37 | 2025-01-06 |  |  |  |  | 1v | 1i Prep/Cam test | [6 empty] | 37 | 37 | 28 |  |  | 28 |  | 4 |  |  | 5
Month 9 | 38 | 2025-01-13 |  |  |  | BLOCK 1 | 1v | 2i Interviews | [5 empty] | Publicity Photos | 38 | 38 | 29 |  |  | 29 |  |  |  |  | 6
2025-01-06 | 39 | 2025-01-20 |  |  |  |  | 1v | Wrap | [6 empty] | 39 | 39 | 30 |  |  | 30 |  |  |  |  | 7
| 40 | 2025-01-27 |  |  |  |  | 1v | [7 empty] | 40 | 40 | 31 |  |  | 31 |  |  |  |  | 8
| 41 | 2025-02-03 |  |  |  |  | 1v | [7 empty] | 41 | 41 | 32 |  |  | 32 |  |  |  |  | 9
Month 10 | 42 | 2025-02-10 |  |  |  |  | 1v | Prep | [6 empty] | 42 | 42 | 33 |  |  | 33 |  |  |  |  | 10
2025-02-03 | 43 | 2025-02-17 |  |  |  | BLOCK 2 | 1v | 3i Interviews | [5 empty] | Publicity Photos | 43 | 43 | 34 |  |  | 34 |  |  |  |  | 11
| 44 | 2025-02-24 |  |  |  |  | 1v | Wrap | [6 empty] | 44 | 44 | 35 |  |  | 35 |  |  |  |  | 12
| 45 | 2025-03-03 |  |  |  |  | 1v | [7 empty] | 45 | 45 | 36 |  |  | 36 |  |  |  |  | 13
Month 11 | 46 | 2025-03-10 |  |  |  |  | 1v | [7 empty] | 46 | 46 | 37 |  |  | 37 |  |  |  |  | 14
2025-03-03 | 47 | 2025-03-17 |  |  |  |  | 1v | Prep | [6 empty] | 47 | 47 | 38 |  |  | 38 |  |  |  |  | 15
| 48 | 2025-03-24 |  |  |  | BLOCK 3 | 1v | 3i Interviews | [5 empty] | Publicity Photos | 48 | 48 | 39 |  |  | 39 |  |  |  |  | 16
| 49 | 2025-03-31 |  |  |  |  | 1v | Wrap | Start Edit | 1 |  |  |  |  | 49 | 49 | 40 |  |  | 40 |  |  |  | 1 | 17
| 50 | 2025-04-07 |  |  |  |  | 1v |  |  | 2 |  |  |  |  | 50 | 50 | 41 |  |  | 41 |  |  |  | 2 | 18
Month 12 | 51 | 2025-04-14 |  |  |  |  | 1v |  |  | 3 |  |  |  |  | 51 | 51 | 42 |  |  | 42 |  |  |  | 3 | 19
2025-04-07 | 52 | 2025-04-21 |  |  |  |  | 1v | Prep |  | 4 |  |  |  |  | 52 | 52 | 43 |  |  | 43 |  |  |  | 4 | 20
| 53 | 2025-04-28 |  |  |  | BLOCK 4 | 1v | 2i Interviews |  | 5 |  |  |  | Publicity Photos | 53 | 53 | 44 |  |  | 44 |  |  |  | 5 | 21
| 54 | 2025-05-05 |  |  |  |  | 1v | Wrap |  | 6 |  |  |  |  | 54 | 54 | 45 |  |  | 45 |  |  |  | 6 | 22
Month 13 | 55 | 2025-05-12 |  |  |  |  | 1v |  |  | 7 |  |  |  |  | 55 | 55 | 46 |  |  | 46 |  |  |  | 7 | 23
2025-05-05 | 56 | 2025-05-19 |  |  |  |  | 1v |  |  | 8 |  |  |  |  | 56 | 56 | 47 |  |  | 47 |  |  |  | 8 | 24
| 57 | 2025-05-26 |  |  |  |  | 1v |  |  | 9 |  |  |  |  | 57 | 57 | 48 |  |  | 48 |  |  |  | 9 | 25
| 58 | 2025-06-02 |  |  |  |  | 1v |  |  | 10 |  |  |  |  | 58 | 58 | 49 |  |  | 49 |  |  |  | 10 | 26
Month 14 | 59 | 2025-06-09 |  |  |  |  | 1v |  |  | 11 |  |  |  |  | 59 | 59 | 50 |  |  | 50 |  |  |  | 11 | 27
2025-06-02 | 60 | 2025-06-16 |  |  | Archive needs? |  | 1v |  |  | 12 |  |  |  |  | 60 | 60 | 51 |  |  | 51 |  | 5 |  | 12 | 28
| 61 | 2025-06-23 |  |  |  |  | 1v |  |  | 13 |  |  |  |  | 61 | 61 | 52 |  |  | 52 |  |  |  | 13 | 29
| 62 | 2025-06-30 |  |  |  |  | 1v |  |  | 14 |  |  |  |  | 62 | 62 | 53 |  |  | 53 |  |  |  | 14 | 30
| 63 | 2025-07-07 |  |  |  |  | 1v |  | 1st Assembly | 15 |  |  |  |  | 63 | 63 | 54 |  |  | 54 |  |  |  | 15 | 31
Month 15 | 64 | 2025-07-14 |  |  |  |  | 1v |  |  | 16 | Composers | Graphics |  |  | 64 | 64 | 55 |  |  | 55 |  |  |  | 16 | 32
2025-07-07 | 65 | 2025-07-21 |  |  |  |  | 1v |  |  | 17 | kickoff mtg | kickoff mtg |  |  | 65 | 65 | 56 |  |  | 56 |  |  |  | 17 | 33
| 66 | 2025-07-28 |  |  |  |  | 1v |  |  | 18 |  |  |  |  | 66 | 66 | 57 |  |  | 57 |  |  |  | 18 | 34
| 67 | 2025-08-04 |  |  |  |  | 1v |  |  | 19 |  |  |  |  | 67 | 67 | 58 |  |  | 58 |  |  |  | 19 | 35
Month 16 | 68 | 2025-08-11 |  |  |  |  | 1v |  |  | 20 |  |  |  |  | 68 | 68 | 59 |  |  | 59 |  |  |  | 20 | 36
2025-08-04 | 69 | 2025-08-18 |  | Fact-check |  |  | 1v |  | Cut 1 | 21 |  |  |  |  | 69 | 69 | 60 |  |  | 60 |  |  |  | 21 | 37
| 70 | 2025-08-25 |  | Cut 1 |  |  | 1v |  |  | 22 | Begin | Begin |  |  | 70 | 70 | 61 |  |  | 61 |  |  |  | 22 | 38
| 71 | 2025-09-01 | [7 empty] | 23 | collaboration | collaboration |  | Festival/Distribution | 71 | 71 | 62 |  |  | 62 |  |  |  | 23 | 39
Month 17 | 72 | 2025-09-08 |  |  | Archive needs? |  |  |  |  | 24 | w/composers | w/graphics |  | Strategy | 72 | 72 | 63 |  |  | 63 |  | 6 |  | 24 | 40
2025-09-01 | 73 | 2025-09-15 |  | Fact-check | [5 empty] | 25 |  |  |  |  | 73 | 73 | 64 |  |  | 64 |  |  |  | 25 | 41
| 74 | 2025-09-22 |  | Cut 2 | [5 empty] | 26 | Temp score? | Temp graphics? |  |  | 74 | 74 | 65 |  |  | 65 |  |  |  | 26 | 42
| 75 | 2025-09-29 | [6 empty] | Cut 2 | 27 |  |  |  |  | 75 | 75 | 66 |  |  | 66 |  |  |  | 27 | 43
| 76 | 2025-10-06 | [7 empty] | 28 |  |  |  |  | 76 | 76 | 67 |  |  | 67 |  |  |  | 28 | 44
Month 18 | 77 | 2025-10-13 | [7 empty] | 29 |  |  |  |  | 77 | 77 | 68 |  |  | 68 |  |  |  | 29 | 45
2025-10-06 | 78 | 2025-10-20 | [7 empty] | 30 |  |  |  |  | 78 | 78 | 69 |  |  | 69 |  |  |  | 30 | 46
| 79 | 2025-10-27 | [7 empty] | 31 |  |  |  |  | 79 | 79 | 70 |  |  | 70 |  |  |  | 31 | 47
| 80 | 2025-11-03 |  |  | Archive needs? |  |  |  |  | 32 | Temp score (%) | Temp graphics (%) |  |  | 80 | 80 | 71 |  |  | 71 |  | 7 |  | 32 | 48
Month 19 | 81 | 2025-11-10 |  | Final |  |  |  |  | Cut 3 | 33 |  |  |  |  | 81 | 81 | 72 |  |  | 72 |  |  |  | 33 | 49
2025-11-03 | 82 | 2025-11-17 |  | fact-check | [5 empty] | 34 |  |  |  |  | 82 | 82 | 73 |  |  | 73 |  |  |  | 34 | 50
| 83 | 2025-11-24 |  | script | [5 empty] | 35 |  |  |  |  | 83 | 83 | 74 |  |  | 74 |  |  |  | 35 | 51
| 84 | 2025-12-01 | [7 empty] | 36 |  |  |  |  | 84 | 84 | 75 |  |  | 75 |  |  |  | 36 | 52
Month 20 | 85 | 2025-12-08 |  |  | Archival |  |  |  |  | 37 | Temp score | Temp graphics |  |  | 85 | 85 | 76 |  |  | 76 |  | 8 |  | 37 | 53
2025-12-01 | 86 | 2025-12-15 |  |  | licensing & master clips |  |  |  | Cut 4 (Fine Cut) | 38 |  |  |  |  | 86 | 86 | 77 |  |  | 77 |  | 9 |  | 38 | 54
| 87 | 2025-12-22 | [7 empty] | 39 |  |  |  |  | 87 | 87 | 78 |  |  | 78 |  | 2.0785 |  | 39 | 55
| 88 | 2025-12-29 | [6 empty] | Deliver Picture | 40 |  |  |  |  | 88 | 88 | 79 |  |  | 79 |  | months |  | 40 | 56
| 89 | 2026-01-05 | [6 empty] | Wrap edit room |  | Final composing | Post | 1 | Trailer, key art, | 89 | 89 | 80 |  |  | 80 |  |  |  | 9.2379 | 57
Month 21 | 90 | 2026-01-12 | [6 empty] | AE post prep |  |  | (12 wks) | 2 | social clips, | 90 | 90 | 81 |  |  | 81 |  |  |  | months | 58
2026-01-05 | 91 | 2026-01-19 | [10 empty] | 3 | press materials | 91 | 91 | 82 |  |  | 82 |  |  |  |  | 59
| 92 | 2026-01-26 | [8 empty] | Finalize music |  | 4 |  | 92 | 92 | 83 |  |  | 83 |  |  |  |  | 60
| 93 | 2026-02-02 | [8 empty] | Arrange |  | 5 |  | 93 | 93 | 84 |  |  | 84 |  |  |  | 0.6 | 61
Month 22 | 94 | 2026-02-09 | [8 empty] | Record |  | 6 |  | 94 | 94 | 85 |  |  | 85 |  |  |  |  | 62
2026-02-02 | 95 | 2026-02-16 | [8 empty] | Music Mix |  | 7 |  | 95 | 95 | 86 |  |  | 86 |  |  |  |  | 63
| 96 | 2026-02-23 | [10 empty] | 8 |  | 96 | 96 | 87 |  |  | 87 |  |  |  |  | 64
| 97 | 2026-03-02 | [10 empty] | 9 |  | 97 | 97 | 88 |  |  | 88 |  |  |  |  | 65
Month 23 | 98 | 2026-03-09 | [10 empty] | 10 |  | 98 | 98 | 89 |  |  | 89 |  |  |  |  | 66
2026-03-02 | 99 | 2026-03-16 | [10 empty] | 11 |  | 99 | 99 | 90 |  |  | 90 |  |  |  |  | 67
| 100 | 2026-03-23 | [10 empty] | 12 |  | 100 | 100 | 91 |  |  | 91 |  |  |  |  | 68
| 101 | 2026-03-30 | [9 empty] | QC & Delivery | 13 |  | 101 | 101 | 92 |  |  | 92 |  |  |  |  | 69
| 102 | 2026-04-06 | [9 empty] | (4 wks) | 14 |  | 102 | 102 | 93 |  |  | 93 |  |  |  |  | 70
Month 24 | 103 | 2026-04-13 | [10 empty] | 15 |  | 103 | 103 | 94 |  |  | 94 |  |  |  |  | 71
2026-04-06 | 104 | 2026-04-20 | [10 empty] | 16 |  | 104 | 104 | 95 |  |  | 95 |  |  |  |  | 72
| 105 | 2026-04-27 | [11 empty] | READY TO | 24.0185 | 24.0185 | 21.94 |  |  | 21.94 |  |  |  |  | 16.6282
[14 empty] | PREMIERE | months | months | months |  |  | months |  |  |  |  | months
Formulas:
MONDAY DATE = [MONDAY DATE, row above]+7

## 3. Budget Globals
0 |  |  | BUDGET GRAND TOTAL: | 1286182.024
| BUDGET GLOBALS |  |  |  | INSTRUCTIONS: "Globals" are used for numbers that will be needed frequently in your budget, like the number of shooting days or the number of edit weeks. Instead of entering these numbers on dozens of lines in the budget, you can enter them once here and then use them "globally" throughout the budget. This makes adjustments easier and can save work and help prevent mistakes. For example, the number of interview shoot days is defined as "SHOOTINTW_DAYS" in cell C6. The word SHOOTINTW_DAYS is then used in formulas throughout the budget and, whenever you want to change the number of interview shoot days, you can just change the value in cell C6, and the budget will recalculate automatically. This is much more efficient than updating multiple budget lines. Two simple examples of formulas using Globals are shown below. To see how Globals are defined, or to create additional Globals yourself, here's an example: click on cell C6, which contains the number of interview shoot days. In the "name box" on the upper left, to the left of the formula bar and below the file menu, you will see the word SHOOTINTW_DAYS. This is where the name is defined and where you can define new names (if the cell didn't have a name, you would just see the cell number C6 in the name box). Alternately, you can access these names in Google Sheets via the menu DATA > NAMED RANGE. To help you quickly see the impact of changing a Global, the BUDGET GRAND TOTAL is shown on the top-right of this tab.
Remember: the numbers of days, weeks or months entered here should match your schedule.
| GLOBAL NAME | AMOUNT | DESCRIPTION
| SHOOTINTW_DAYS | 10 | days shooting interviews
| SHOOTVIS_DAYS | 53 | days shooting visuals
| SOUND_DAYS | 10 | days w/sound recordist
| BCAM_DAYS | 0 | days w/ additional "B" camera
| RESEARCH_WEEKS | 18 | weeks research
| PREP_WEEKS | 9 | weeks pre-production ("prep")
| OVERLAP1 | -9 | weeks research/prep overlap
| PROD_WEEKS | 52 | weeks production
| EDIT_WEEKS | 40 | weeks editing
| OVERLAP2 | -22 | weeks prod/edit overlap
| FINISH_WEEKS | 16 | weeks finishing
| TOTAL_WEEKS | 104 | weeks total
| TOTAL_MONTHS | 24.0185 | months total
| CONTINGENCY | 7.5% | Contingency
| MISC | 150 | Miscellaneous
| FISCAL | 5% | Fiscal Sponsor Fees
Payroll taxes and costs (calculated for New York State, USA)*
| FRINGE | 18.35% | FICA, Medicare, Workers Comp, Payroll, FUTA, NYS SUTA+RS
| *This is the detailed breakdown of New York State payroll taxes/costs (see note below). You will need to research the taxes, social security and other costs that apply to employees wherever you are based/working. |  |  |  | ***EXAMPLE*** | 10 | <<< the formula in this cell uses "SHOOTINT_DAYS" to show the number of interview shoot days
| Employer Social Security rate is 6.2% |  |  |  | ***EXAMPLE*** | 56 | <<< the formula in this cell adds the edit weeks (EDIT_WEEKS) and the post/finishing weeks (FINISH_WEEKS)
Employer Medicare rate is 1.45%
Federal Unemployment (FUTA) is .6%
NYS Unemployment (SUTA) varies but is 4.025% for new employers
NYS Re-employment Svc (RS) Fund - .075%
Note: there are some additional technicalities to USA payroll costs, such as applying wage based limits, that are beyond the scope of this budget template. More importantly though, the simple percentage-based approach used here is also the safer approach because it protects you in case employees are replaced midway through the production, or salaries are spread across multiple calendar years, which would potentially eliminate any savings you might have realized with a more complicated calculation.

## 4. Budget Detail
0 | ACCT | DESCRIPTION | # | UNIT | X | RATE | TOTAL $ COST | 1286182.024
(*DO NOT PRINT | [7 empty] | (*DO NOT PRINT
THIS COLUMN*) | [7 empty] | THIS COLUMN*)
UNTITLED EXCELLENT DOCUMENTARY FILM
BUDGET DATE: 3/1/2024
| PRODUCTION COMPANY: Great Docu Films Inc. |  |  | Research: | 18 | weeks
| DIRECTOR : Excellent Director |  |  | Prep: | 9 | weeks (overlaps with research)
| PRODUCER: Excellent Producer |  |  | Shoot Days: | 12 interview days+53 vérité days
| EDITOR: Super Cutter |  |  | Shoot/Production Period: | 52 | weeks
| LINE PRODUCER: OnBudget Smithee |  |  | Edit: | 40 | weeks (overlaps with shoot)
|  |  |  | Finishing/Post: | 16 | weeks
| BUDGET PREPARED BY: OnBudget Smithee |  |  | TOTAL WEEKS: | 104 | weeks
|  |  |  | TOTAL MONTHS: | 24.0185 | months
| LENGTH: 95 min (approx.) |  |  | DELIVERY DATE: | TBD
Original Footage: 90 min
| Archival Footage: 3 min |  |  | LOCATIONS: | New York, Los Angeles, Houston
| Graphics/Animation: 2 min (Opening title, End credits) |  |  | UNION/GUILD: | Non-Union
| SHOOTING FORMAT: 4K UHD |  |  | ADDITIONAL NOTE #1:
| EDITING FORMAT: Avid DNX36 offline |  |  | ADDITIONAL NOTE #2:
| FINISHING FORMAT: 4K UHD (Quicktime, IMF, DCP) |  |  | ADDITIONAL NOTE #3:
| 1000 | STORY RIGHTS, RESEARCH & PROJECT DEVELOPMENT | # | UNIT | X | RATE | TOTAL $ COST
| 1000 | STORY & OTHER RIGHTS |  |  |  |  | 0
| 1010 | Story Rights-Option |  | flat | 1 | 0 | 0
| 1020 | Story Rights-Purchase |  | flat | 1 | 0 | 0
| 1090 | Miscellaneous |  | allow | 1 | 150 | 0
| 1100 | RESEARCH |  |  |  |  | 1600
| 1110 | Books | 1 | allow | 1 | 100 | 100
| 1120 | Videos, Screenings | 1 | allow | 1 | 100 | 100
| 1130 | Research Meetings | 1 | allow | 1 | 250 | 250
| 1140 | Research Consultants (subject-area experts, legal, archive, impact, etc.) | 2 | days | 1 | 500 | 1000
| 1190 | Misc Research | 1 | allow | 1 | 150 | 150
| 1200 | RESEARCH TRAVEL
|  | RESEARCH TRIP #1: Dir, Prod travel NYC->Houston for 2 nights |  |  |  |  | 2110
| 1210 | Airfare/Railfare | 2 | R/T | 1 | 340 | 680
| 1220 | Add'l Baggage Fees for equipment | 0 | fees | 1 | 50 | 0
| 1230 | Hotel/Lodging | 2 | hotel-nights | 2 | 200 | 800
| 1240 | Local Transport/Taxis/Car Service/Car Rental/Public Transport | 2 | days | 1 | 100 | 200
| 1250 | Meals & Per Diem | 2 | days | 2 | 70 | 280
| 1280 | Accessibility for Travel (Accessibility requirements could include a flight upgrade for more accessible seating, mobility equipment, car service instead of public transport, wheelchair van/lift, or assistance from a personal assistant, rest days, etc.) |  | allow | 1 | 500 | 0
| 1290 | Misc Research Travel | 1 | allow | 1 | 150 | 150
| 1300 | WRITTEN PROPOSAL, BUDGET/SCHEDULE, OTHER FUNDRAISING COSTS |  |  |  |  | 800
| 1310 | Written Treatment/Proposal (grant writer) |  | allow | 1 | 2500 | 0
| 1320 | Fundraising/Pitch Deck |  | allow | 1 | 1500 | 0
| 1330 | Budget/Schedule |  | allow | 1 | 2500 | 0
| 1340 | Cashflow |  | allow | 1 | 1000 | 0
| 1350 | Printed materials, one-sheets, postcards, etc. | 1 | allow | 1 | 250 | 250
| 1360 | Fees for attending markets | 1 | fees | 1 | 400 | 400
| 1390 | Misc fundraising costs & materials | 1 | allow | 1 | 150 | 150
| 1400 | PRODUCTION OF "TEST SHOOTS" OR "SPECIAL SHOOTS" FOR SAMPLE TEASER |  |  |  |  | 0
Only use this section if you are doing special shoots that are only for the fundraising sample teaser. If the material for the sample teaser will come from your early footage and not from special shoots, budget for that as normal, below in the main production section.
| 1401 | Director/Writer/Co-Producer |  | flat | 1 | 2000 | 0
| 1402 | Producer/Writer |  | flat | 1 | 2000 | 0
| 1404 | Director of Photography |  | days | 1 | 900 | 0
| 1405 | Sound |  | days | 1 | 700 | 0
| 1409 | Production Assistants |  | days | 1 | 200 | 0
| 1420 | Talent |  | allow | 1 | 0 | 0
| 1430 | Camera/Lighting/Grip Equipment Rental |  | days | 1 | 600 | 0
| 1431 | Sound Equipment Rental |  | days | 1 | 350 | 0
| 1432 | Other Production Expenses |  | days | 1 | 1000 | 0
| 1440 | Insurance |  | allow | 1 | 2000 | 0
| 1450 | Office & Admin |  | allow | 1 | 500 | 0
| 1480 | Accessibility for Test/Special Shoots (Accessibility requirements can vary. See 5380 and 5880 for details) |  | allow | 1 |  | 0
| 1490 | Miscellaneous |  | allow | 1 | 150 | 0
| 1498 | Union and Guild Fees |  | % | 1 | 0 | 0
| 1499 | Personnel Taxes (FICA, Medicare, Workers Comp, FUTA, NYS SUTA+RS, Payroll) | 0 | payroll | 1 | 18.35% | 0
| 1500 | EDITING & POST-PRODUCTION FOR SAMPLE TEASER |  |  |  |  | 4715.15
| 1510 | Editor (contractor) | 1 | weeks | 1 | 3000 | 3000
| 1520 | Assistant Editor | 0.6 | weeks | 1 | 1500 | 900
| 1530 | Edit Room Rental + Editorial Expenses | 1 | weeks | 1 | 500 | 500
| 1540 | Online/Conform/Color/Graphics (none, finished on edit system) | 0 | allow | 1 | 0 | 0
| 1541 | Music (none, composers offered previous tracks) | 0 | allow | 1 | 0 | 0
| 1542 | Sound Edit/Mix (none, finished on edit system) | 0 | allow | 1 | 0 | 0
| 1543 | Closed Captioning (CC) (temp burn-in subs from edit system) | 0 | minute | 1 | 15 | 0
| 1544 | Audio Description Services (temp track from edit team) | 0 | minute | 1 | 45 | 0
| 1545 | Transcript (including all audible and visual elements) (In-house) |  | cuts | 1 | 150 | 0
| 1580 | Accessibility for Editing/Post for Sample Teaser |  | allow | 1 |  | 0
| 1590 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 1599 | Personnel Taxes (FICA, Medicare, Workers Comp, FUTA, NYS SUTA+RS, Payroll) | 900 | payroll | 1 | 18.35% | 165.15
| 1600 | FUNDRAISING TRAVEL |  |  |  |  | 1390
FUNDRAISING TRIP #1: Producer travel NYC -> LA for meetings/pitch
| 1610 | Airfare/Railfare | 1 | R/T | 1 | 400 | 400
| 1620 | Add'l Baggage Fees for equipment | 0 | fees | 1 | 50 | 0
| 1630 | Hotel/Lodging | 2 | hotel-nights | 1 | 250 | 500
| 1640 | Local Transport/Taxis/Car Service/Car Rental/Public Transport | 2 | days | 1 | 100 | 200
| 1650 | Meals & Per Diem | 2 | days | 1 | 70 | 140
| 1680 | Accessibility for Travel (see 1280 for details) |  | allow | 1 | 500 | 0
| 1690 | Misc Fundraising Travel | 1 | allow | 1 | 150 | 150
|  | TOTAL |  |  |  |  | 10615.15
| 2000 | PRODUCING STAFF | # | UNIT | X | RATE | TOTAL $ COST
| 2000 | DIRECTORS, PRODUCERS, WRITERS |  |  |  |  | 245000
| 2010 | Director/Writer/DOP/Co-Producer (approx. $60k/yr or $5k/month for 24 mos.) (contractor) | 1 | allow | 1 | 120000 | 120000
| 2020 | Producer/Writer/Sound (approx. $60k/yr or $5k/month for 24 mos.) (contractor) | 1 | allow | 1 | 120000 | 120000
| 2030 | Executive Producer |  | flat | 1 | 0 | 0
| 2040 | Co-Producer |  | flat | 1 | 0 | 0
| 2050 | Associate Producer |  | week | 1 | 1500 | 0
| 2060 | Writer |  | flat | 1 | 0 | 0
| 2080 | Accessibility for Directors, Producers, Writers (Accessibility requirements will vary and could include an ASL interpreter, note-taker, assistance from a personal assistant, more time or rest time during shoots, rest space, quiet space, interpreter rest space, service animal rest space, mobility equipment, screenreaders, accessible toilets, etc.) | 1 | allow | 1 | 5000 | 5000
| 2098 | Union and Guild Fees |  | payroll | 1 | 0 | 0
| 2099 | Personnel Taxes (FICA, Medicare, Workers Comp, FUTA, NYS SUTA+RS, Payroll) |  | payroll | 1 | 18.35% | 0
|  | TOTAL |  |  |  |  | 245000
| 3000 | TALENT | # | UNIT | X | RATE | TOTAL $ COST
| 3000 | TALENT |  |  |  |  | 0
| 3010 | Actors (i.e. on screen re-creations) |  | days | 1 | 783 | 0
| 3020 | Voice Actors |  | hours | 1 | 100 | 0
| 3030 | Narrator |  | days | 1 | 783 | 0
| 3040 | Casting Director |  | flat | 1 | 0 | 0
| 3050 | Voice Actor Contractor Fee (coordinate 3-8 voice actors, 4hr session) |  | flat |  | 600 | 0
| 3080 | Accessibility for Talent (see 2080 for details) | 0 | allow | 1 | 0 | 0
| 3097 | Talent Agency Fees | 0 | payroll | 1 | 10% | 0
| 3098 | Union & Guild Fees (SAG P&H) | 0 | payroll | 1 | 21% | 0
| 3099 | Personnel Taxes (FICA, Medicare, Workers Comp, FUTA, NYS SUTA+RS, Payroll) | 0 | payroll | 1 | 18.35% | 0
|  | TOTAL |  |  |  |  | 0
| ATL | SUBTOTAL ABOVE-THE-LINE (ATL) |  |  |  |  | 255615.15 | 19.87%
|  | STAFF | # | UNIT | X | RATE | TOTAL $ COST
| 4000 | PRODUCTION STAFF |  |  |  |  | 180536.72
| 4010 | Line Producer (half-time) |  | weeks |  | 2500 | 0
| 4012 | Unit Production Manager | 95 | weeks | 0.6 | 1600 | 91200
| 4015 | Production Coordinator |  | weeks | 1 | 1200 | 0
| 4020 | Post Production Supervisor |  | weeks | 1 | 2000 | 0
| 4025 | Post Production Coordinator |  | weeks | 1 | 1200 | 0
| 4030 | Accessibility Coordinator/ Production Access Coordinator
|  | Pre-Production | 5 | days | 1 | 450 | 2250
|  | Production | 3 | days | 1 | 450 | 1350
|  | Post-Production | 4 | days | 1 | 450 | 1800
| 4040 | Production Accountant (see 9300 Professional Services) | 0 | days | 1 | 250 | 0
| 4050 | Story/Investigative Researcher | 0 | weeks | 1 | 1400 | 0
| 4060 | Archival Producer |  | weeks | 1 | 2100 | 0
| 4065 | Archival Researcher (part-time 2dys/wk) | 9 | weeks | 0.4 | 1700 | 6120
| 4070 | Office Production Assistant (PA1) | 95 | weeks | 0.6 | 800 | 45600
| 4080 | Accessibility for Production Staff (see 2080 for details) | 1 | allow | 1 | 5000 | 5000
| 4098 | Union & Guild Fees |  | allow | 1 | 0 | 0
| 4099 | Personnel Taxes (FICA, Medicare, Workers Comp, FUTA, NYS SUTA+RS, Payroll) | 148320 | salary | 1 | 18.35% | 27216.72
| 4100 | PRODUCTION CREW (10hrs/shoot day) |  |  |  |  | 87332.15
| 4110 | Director of Photography
|  | Prep | 1 | days | 1 | 900 | 900
|  | Location Scout | 2 | days | 1 | 900 | 1800
|  | Camera Test | 1 | days | 1 | 900 | 900
|  | Interviews | 10 | days | 1 | 900 | 9000
|  | Visuals/Verite (Director/DOP will shoot) | 53 | days | 1 | 0 | 0
|  | Aerials/Drone (DP supervise Drone/Aerials listed inder 5060) | 0 | days | 1 | 900 | 0
|  | Color Grading | 1 | days | 1 | 900 | 900
| 4112 | "B" Camera Operator | 0 | days | 1 | 800 | 0
| 4113 | Steadicam Operator |  | days | 1 | 0 | 0
| 4114 | Unit Still Photographer | 2 | days | 1 | 650 | 1300
| 4115 | Assistant Camera/Focus Puller
|  | Equipment Check-Out | 4 | days | 1 | 650 | 2600
|  | Camera Test | 1 | days | 1 | 650 | 650
|  | Interviews | 10 | days | 1 | 650 | 6500
|  | Visuals/Verite |  | days | 1 | 650 | 0
| 4117 | Digital Image Technician (DIT) |  | days | 1 | 750 | 0
| 4118 | Data Wrangler
|  | Camera Test | 1 | days | 1 | 550 | 550
|  | Interviews | 10 | days | 1 | 550 | 5500
|  | Visuals/Verite | 53 | days | 0.33333 | 550 | 9716.6667
| 4120 | Gaffer
|  | Prep/Equipment Check-Out | 0 | days | 1 | 750 | 0
|  | Camera Test | 1 | days | 1 | 750 | 750
|  | Interviews | 10 | days | 1 | 750 | 7500
|  | Visuals/Verite |  | days | 1 | 750 | 0
| 4122 | Electrician/Swing
|  | Prep/Equipment Check-Out | 4 | days | 1 | 450 | 1800
|  | Camera Test | 1 | days | 1 | 450 | 450
|  | Interviews | 10 | days | 1 | 450 | 4500
|  | Visuals/Verite |  | days | 1 | 450 | 0
| 4123 | Key Grip |  | days | 1 | 450 | 0
| 4125 | Dolly Grip |  | days | 1 | 700 | 0
| 4130 | Sound Recordist
|  | Camera Test | 1 | days | 1 | 750 | 750
|  | Interviews | 10 | days | 1 | 750 | 7500
|  | Visuals/Verite (Producer/Sound will do sound) | 53 | days | 1 | 0 | 0
| 4140 | Art Director |  | days | 1 | 750 | 0
| 4150 | Hair/Makeup/Wardrobe Stylist w/kit |  |  |  |  | 0
|  | Interviews | 10 | days | 1 | 400 | 4000
| 4160 | Set Production Assistants
|  | Set Production Assistant #1 (Office Assistant from 4060 will be Set PA1) |  | weeks | 1 |  | 0
|  | Set Production Assistant #2 (On-Set) | 10 | days | 1 | 200 | 2000
| 4170 | Security Guards |  | days | 1 | 320 | 0
| 4180 | Accessibility for Production Crew (see 2080 for details) | 1 | allow | 1 | 5000 | 5000
| 4198 | Union & Guild Fees |  | allow | 1 | 0 | 0
| 4199 | Personnel Taxes (FICA, Medicare, Workers Comp, FUTA, NYS SUTA+RS, Payroll) | 69566.6667 | salary | 1 | 18.35% | 12765.4833
| 4200 | EDITORIAL STAFF |  |  |  |  | 271108.7
| 4210 | Editor (independent contractor)
|  | Prep/consult during shoot | 0.2 | week | 1 | 3300 | 660
|  | Edit period (per ADE guideline 1 month per 10 min screen time) | 40 | weeks | 1 | 3300 | 132000
|  | Post sound, online, color correction | 0.2 | weeks | 1 | 3300 | 660
|  | Re-cut one-hour TV version | 0 | weeks | 1 | 3300 | 0
| 4220 | Consulting Editors |  | days | 1 | 1000 | 0
| 4230 | Assistant Editor
|  | Setup edit room & system | 1 | weeks | 1 | 1700 | 1700
|  | Log/capture/ingest all footage during shoot | 15 | weeks | 1 | 1700 | 25500
|  | Edit period | 40 | weeks | 1 | 1700 | 68000
|  | Wrap edit/prep post | 4 | weeks | 1 | 1700 | 6800
|  | Post sound, online, color correction (half-time) | 12 | weeks | 0.5 | 1700 | 10200
| 4280 | Accessibility for Editorial Staff (see 2080 for details) | 1 | allow | 1 | 5000 | 5000
| 4298 | Union & Guild Fees | 0 | allow | 1 | 0 | 0
| 4299 | Personnel Taxes (FICA, Medicare, Workers Comp, FUTA, NYS SUTA+RS, Payroll) | 112200 | salary | 1 | 18.35% | 20588.7
| 4300 | CONSULTANTS |  |  |  |  | 0
| 4310 | Honoraria for subject-area experts/consultants |  | day | 1 | 500 | 0
| 4320 | Honoraria for advisory board members (approx. 3 dys total per person @ $500/dy) |  | flat | 3 | 500 | 0
| 4330 | Trauma-informed mental health and wellness support for film team |  | day | 1 | 450 | 0
| 4340 | Trauma-informed mental health and wellness support for participants (incl. on-set) |  | day | 1 | 450 | 0
| 4350 | Participant care/compensation (Check funder/distributor policies and current industry standards before budgeting these items. Could include per diem, location fees, materials fees, reimbursement for missed wages, childcare, mental health support, and/or direct compensation) |  | day | 1 |  | 0
| 4380 | Accessibility for Consultants (see 2080 for details) |  | allow | 1 |  | 0
|  | TOTAL |  |  |  |  | 538977.57
|  | PRODUCTION EXPENSES | # | UNIT | X | RATE | TOTAL $ COST
| 5000 | CAMERA |  |  |  |  | 26402
| 5010 | Camera Package Rentals
MAIN PACKAGE (all days)
|  | SONY FX9 CAMERA PACKAGE: Sony FX9 XDCAM Full Frame Camera, camera cage, base plate, 240GB XQD cards, XQD card reader, BP-U 98Wh batteries, BP-U dual-bay battery charger, Pelican case, support backpack, cables, accesories Note: due to the number of shooting days, camera package rental at the appropriate rate of $350/day ($350/day*(12dys+53dys) = $22,750) would exceed the purchase price of $18,686. Because it is being rented directly from the production company, the price is capped at 75% of the purchase price, which controls funder costs (policies and percentage caps vary) and helps the production company earn rental income. If the total rental was less than the funder's percentage cap, or if this were being rented from a commercial rental house, then this would be budgeted as a normal daily rental. | 1 | allow | 0.75 | 18686 | 14014.5
|  | TAMRON LENS PACKAGE: 20-40mm f/2.8, 35-150mm f/2-2.8, 150-500mm f/5-6.7 Per the detailed explanation above, rental at $90/day ($90/day*(12dys+53dys)= $5,850) would exceed the purchase price of $3,700. Instead, because this can be rented from the production company, the rental is capped at 75% of the purchase price or $2,775. | 1 | allow | 0.75 | 3700 | 2775
|  | CAMERA SUPPORT PACKAGE: Heavy Duty Tripod, Shoulder Rig Per the detailed explanation above, rental at $50/day ($50/day*(12dys+53dys)= $3,250) would exceed the purchase price of $2,500. Instead, because this can be rented from the production company, the rental is capped at 75% of the purchase price or $1,875. | 1 | allow | 0.75 | 2500 | 1875
|  | ADDITIONAL RENTALS (interview days) | 10 | days | 1 | 450 | 4500
Angenieux EZ-1 30 to 90mm Cinema Lens (Super35 T2.0 and Full-Frame T3.0)
External monitors, clip-on matte box, filters, follow focus, rods, plates, etc.
ADDITIONAL SPECIALTY RENTALS
Specialty cameras
Dollys and sliders
Steadicam package
Car mount
| 5020 | Camera purchases |  | allow | 1 |  | 0
| 5030 | Camera expendables | 1 | allow | 1 | 500 | 500
| 5040 | DIT/Data Station rentals |  | allow | 1 |  | 0
| 5050 | DIT/Data Station purchases
|  | M3 Max MBPro 16" Laptop (buy/sell at end of production) | 1 | allow | 0.5 | 3500 | 1750
|  | UPS Uninterruptible Power Supply (buy/sell at end of production) | 1 | allow | 0.5 | 75 | 37.5
|  | Pelican cases (buy/sell at end of production) | 2 | cases | 0.5 | 300 | 300
|  | Software (Silverstack, Offshoot etc.) | 1 | year | 1 | 500 | 500
(field drives listed below in 5700)
| 5060 | Drone/aerial photography |  | days | 1 | 1500 | 0
| 5080 | Accessibility incl. additional monitors or cameras, wheelchair mounts, etc. |  | allow | 1 |  | 0
| 5090 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 5100 | SOUND |  |  |  |  | 6271
| 5110 | Sound kit/equipment rentals
|  | Sound recordist kit rental for interview days | 10 | days | 1 | 250 | 2500
|  | Sound in-house kit (Prod does sound on verite/visuals days) | 53 | days | 1 | 60 | 3180
| 5120 | Sound kit/equipment purchases | 0 | allow | 1 | 0 | 0
| 5130 | Sound expendables incl. batteries | 63 | days | 1 | 7 | 441
| 5140 | Comtek monitoring system |  | days | 1 |  | 0
| 5150 | Walkie-talkies |  | days | 1 |  | 0
| 5180 | Accessibility incl. additional monitor feeds, bespoke receivers, etc. |  | allow | 1 |  | 0
| 5190 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 5200 | LIGHTING & GRIP |  |  |  |  | 6505
| 5210 | Lighting & grip package rental
|  | Lighting & grip package rental for stylized interviews | 10 | days | 1 | 400 | 4000
|  | Lighting & grip in-house kit for verite/visuals | 53 | days | 1 | 35 | 1855
| 5220 | Lighting & grip purchases | 0 | allow | 1 |  | 0
| 5230 | Lighting & grip expendables | 1 | allow | 1 | 500 | 500
| 5240 | Generator Rental |  | days | 1 |  | 0
| 5290 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 5300 | STUDIO FACILITIES |  |  |  |  | 0
| 5310 | Studio rentals |  | days | 1 | 0 | 0
| 5320 | Studio utilities |  | allow | 1 | 0 | 0
| 5380 | Accessibility for studio facilities (Accessibility requirements will vary and could include additional lighting, floor markings, ramps, rest space, quiet space, interpreter rest space, service animal rest space, bell/light or traffic light system for "All quiet on set", mobility equipment, accessible toilets, etc.) |  | allow | 1 | 1000 | 0
| 5390 | Miscellaneous |  | allow | 1 | 150 | 0
| 5400 | SET DRESSING |  |  |  |  | 0
| 5410 | Set dressing rentals |  | allow | 1 | 0 | 0
| 5420 | Set dressing purchases |  | allow | 1 | 0 | 0
| 5430 | Set dressing expendables |  | allow | 1 | 0 | 0
| 5490 | Miscellaneous |  | allow | 1 | 150 | 0
| 5500 | WARDROBE |  |  |  |  | 0
| 5510 | Wardrobe rentals |  | allow | 1 | 0 | 0
| 5520 | Wardrobe purchases |  | allow | 1 | 0 | 0
| 5530 | Wardrobe expendables |  | allow | 1 | 0 | 0
| 5590 | Miscellaneous |  | allow | 1 | 150 | 0
| 5600 | MAKEUP & HAIR |  |  |  |  | 1000
| 5610 | Makeup rentals (kit rental from M/U artist) | 10 | days | 1 | 75 | 750
| 5620 | Makeup purchases | 1 | allow | 1 | 100 | 100
| 5630 | Makeup expendables |  | allow | 1 | 100 | 0
| 5690 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 5700 | PRODUCTION FILM & LAB |  |  |  |  | 8950
Data storage calculation: Visuals/vérité: 53 dys*120min/approx. 256 GB per day = 106 hours camera footage (13.5TB) Interviews: 10 dys*240min/approx. 512GB = 40 hours camera footage (5TB) Total: 18.5 TB total plus 25% buffer -> Spec minimum 24TB of camera original storage
| 5710 | Field Drives - SanDisk Pro SSD (2 sets) | 6 | 4 TB drives | 2 | 400 | 4800
| 5720 | RAID 4 Master Drive - camera original storage (G-Raid Shuttle 24TB) | 1 | drives | 1 | 1900 | 1900
| 5730 | LTO Backup of all master media |  |  |  |  | 0
|  | LTO-8 backup | 24 | TB | 1 | 40 | 960
|  | LTO Tape Cartridges (1 per month) | 12 | tapes | 1 | 95 | 1140
| 5790 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 5800 | LOCATION EXPENSES |  |  |  |  | 9143
| 5810 | Crew Meals
|  | Interview Days (Dir, Prod, DP, AC, DW, Gf, Snd, PM, PA) | 10 | meals | 9 | 17 | 1530
|  | Verite/Visuals Days (Dir, Prod, PA) | 53 | meals | 3 | 17 | 2703
|  | Allowance for 2nd Meal on Long Days |  | allow | 1 | 0 | 0
| 5820 | Snacks/Craft Service |  |  | 1 |  | 0
|  | Interview Days (Dir, Prod, DP, AC, DW, Gf, Snd, PM, PA) | 10 | days | 1 | 60 | 600
|  | Verite/Visuals Days (Dir, Prod, PA) | 53 | days | 1 | 20 | 1060
| 5850 | First Aid Supplies | 1 | allow | 1 | 100 | 100
| 5860 | Location Fees, Permits, Parking, Gratuities | 1 | allow | 1 | 1000 | 1000
| 5880 | Accessibility for locations (Accessibility requirements will vary and could include additional lighting, floor markings, ramps, rest space, quiet space, interpreter rest space, service animal rest space, bell/light system or traffic light system for "All quiet on set", mobility equipment, accessible toilets, accessible dining location and table height, etc.) | 1 | allow | 1 | 1000 | 1000
| 5885 | Loss, Damage & Repair | 1 | allow | 1 | 1000 | 1000
| 5890 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 5900 | LOCATION TRANSPORTATION |  |  |  |  | 11505
| 5910 | Vehicle rentals
|  | Cargo van - w/high roof+shelving (needed for interview weeks only) | 4 | weeks | 1 | 1100 | 4400
|  | Wheelchair van - w/additional portable wheelchair ramp | 4 | weeks | 1 | 950 | 3800
|  | People mover - minivan (7-9 passengers) or van (15 passengers) |  | weeks | 1 | 800 | 0
|  | Car rentals |  | weeks | 1 | 0 | 0
| 5920 | Vehicle purchases |  | allow | 1 | 0 | 0
| 5930 | Gas & Oil | 4 | weeks | 1 | 300 | 1200
| 5940 | Road Permits, Tolls, Parking | 4 | weeks | 1 | 150 | 600
| 5950 | Local transportation/Taxis/Car Service/Public Transport |  | days | 1 |  | 0
| 5960 | Mileage expense for self-drive vehicles (based on 2024 IRS mileage rate) | 1500 | miles | 1 | 0.67 | 1005
| 5980 | Accessibility for Transportion (Accessibility requirements will vary and could include vehicle accessories, adaptations or modification.) | 1 | allow | 1 | 500 | 500
| 5990 | Miscellaneous |  | allow | 1 | 150 | 0
|  | TOTAL |  |  |  |  | 69776
|  | TRAVEL | # | UNIT | X | RATE | TOTAL $ COST
| 6000 | PRODUCTION TRAVEL |  |  |  |  | 7560
SHOOT TRIP #1: Dir, Prod, DP travel to NYC->Houston for 2 nights
| 6010 | Airfare/Railfare | 3 | R/T | 1 | 340 | 1020
| 6020 | Add'l baggage fees for equipment | 2 | fees | 1 | 50 | 100
| 6030 | Hotel/Lodging | 2 | hotel-nights | 3 | 300 | 1800
| 6040 | Local Transport/Taxis/Car Service/Car Rental/Public Transport | 2 | days | 1 | 100 | 200
| 6050 | Meals & Per Diem | 2 | days | 3 | 70 | 420
| 6080 | Accessibility for Travel (see 1280 for details) |  | allow | 1 | 500 | 0
| 6090 | Misc Travel | 1 | allow | 1 | 150 | 150
SHOOT TRIP #2: Dir, Prod, DP travel to NYC->LA for 2 nights
| 6010 | Airfare/Railfare | 3 | R/T | 1 | 400 | 1200
| 6020 | Add'l baggage fees for equipment | 2 | fees | 1 | 50 | 100
| 6030 | Hotel/Lodging | 2 | hotel-nights | 3 | 300 | 1800
| 6040 | Local Transport/Taxis/Car Service/Car Rental/Public Transport | 2 | days | 1 | 100 | 200
| 6050 | Meals & Per Diem | 2 | days | 3 | 70 | 420
| 6080 | Accessibility for Travel (see 1280 for details) |  | allow | 1 | 500 | 0
| 6090 | Misc Travel | 1 | allow | 1 | 150 | 150
|  | TOTAL |  |  |  |  | 7560
|  | POST-PRODUCTION | # | UNIT | X | RATE | TOTAL $ COST
| 7000 | EDITORIAL EQUIPMENT, FACILITY & SUPPLIES |  |  |  |  | 33850.4884
| 7010 | Editing Equipment Rentals
|  | EDITOR AVID SYSTEM Mac Studio M2 Ultra 24‑core/60‑GPU/32‑Neural/128GB RAM/1TB SSD, Dual Apple 27" 5K Retina Studio Displays, Video Playback Monitor, Blackmagic Design Ultrastudio 4K mini, Audio Interface/Controller, JBL 305P Near-Field Monitor Speakers, Headphones, UPS Uninterruptible Power Supply, Cables & Accessories Note: due to the number of edit weeks, edit system rental at the appropriate rate of $400/week ($400/week*42 weeks=$16,800) would exceed the purchase price of $10,697. Because it is being rented directly from the production company, the price is capped at 75% of the purchase price, which controls funder costs (policies and percentages vary) and helps the production company earn rental income. If the total rental was less than the funder's percentage cap, or if this were being rented from a commercial rental house, then this would be budgeted as a normal weekly rental. | 1 | allow | 0.75 | 10697 | 8022.75
|  | ASSISTANT EDITOR AVID SYSTEM Mac Studio M2 Ultra 24‑core/60‑GPU/32‑Neural/128GB RAM/1TB SSD, Dual Apple 27" 5K Retina Studio Displays, Audio Interface/Controller, JBL 305P Near-Field Monitor Speakers, Headphones, UPS Uninterruptible Power Supply, Cables & Accessories Per the detailed explanation above, rental at $300/week ($300/wk*72 wks = $22,200) would exceed the purchase price of $8,697. Instead, because this can be rented from the production company, the rental is capped at 75% of the purchase price or $6,523. | 1 | allow | 0.75 | 8697 | 6522.75
| 7020 | Editing Equipment Purchases
|  | Editor System - Avid Media Composer Ultimate Software License | 1 | year | 1 | 540 | 540
|  | AE System - Avid Media Composer Ultimate Software License | 2 | years | 1 | 540 | 1080
|  | Other purchases | 1 | allow | 1 | 500 | 500
| 7025 | Edit Storage
|  | Primary storage (G-RAID Shuttle 4 80TB formatted as RAID 5 for 60TB capacity) | 1 | allow | 1 | 3300 | 3300
|  | Backup storage (G-RAID Shuttle 4 80TB formatted as RAID 5 for 60TB capacity) | 1 | allow | 1 | 3300 | 3300
| 7026 | LTO/offsite backup/archiving | 40 | TB | 1 | 80 | 3200
| 7030 | Cloud Services (e.g. Vimeo Pro, Frame.io, PostLab, etc.) | 12.933 | months | 1 | 200 | 2586.6051
| 7035 | Technical support | 1 | allow | 1 | 500 | 500
| 7040 | Edit room rental (see 9070 Production Office rental) (Fully accessible edit room incl. parking, offices, bathrooms, etc. See 7080.) |  | weeks | 2 | 500 | 0
| 7041 | High Speed Internet (see 9080 Production Office rental) |  | months | 1 | 80 | 0
| 7042 | Edit parking (see 9080 Production Office rental) |  | weeks | 3 | 40 | 0
| 7050 | Transcription, Translation & Temp Subtitles/Captions for Cuts & Working Materials |  |  |  |  | 0
|  | 90-min training for in-house team re: logging, transcripts, image description, temp subtitles, captions, audio description, QC | 1 | allow | 1 | 250 | 250
|  | Interview Transcriptions (edit software transcribe+PA1 in-house revise) |  | days | 1 |  | 0
|  | Logging verite footage (PA1 in-house) |  | allow | 1 |  | 0
|  | Temp subtitles for rough cuts (temp burn-in from edit system) |  | minute | 1 | 12 | 0
|  | Temp Closed Captioning (CC) (temp burn-in from edit system) |  | minute | 1 | 15 | 0
|  | Audio Description Services (temp track from edit team) |  | minute | 1 | 45 | 0
|  | Transcript (including all audible and visual elements) Cuts 1-4, (PA1 in-house) |  | cuts | 1 | 300 | 0
| 7060 | Edit office supplies | 12.933 | months | 1 | 80 | 1034.642
| 7065 | Edit meals & craft service (Working Meals/Deadlines) | 9.2379 | months | 1 | 100 | 923.7875
| 7070 | Local Transport (Taxis/Car Service/Car Rental/Mileage/Public Transport) | 12.933 | months | 1 | 150 | 1939.9538
| 7080 | Accessibility for editing (Accessibility requirements will vary and could include a fully wheelchair-accessible edit location, modified desks and/or chairs, screenreaders, accessible toilets, additional lighting, floor markings, rest space, quiet space, interpreter rest space, service animal rest space, etc.) |  | allow | 1 | 0 | 0
| 7090 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 7100 | FORMAT CONVERSIONS |  |  |  |  | 800
| 7110 | Archival Material Ingest | 1 | TB | 1 | 150 | 150
| 7120 | Upconversions to 4K / Create file-based media from archival | 1 | allow | 1 | 500 | 500
| 7190 | Misc. format conversions | 1 | allow | 1 | 150 | 150
| 7200 | GRAPHICS, TITLES & EFFECTS |  |  |  |  | 5150
| 7210 | Main title design | 1 | flat | 1 | 4000 | 4000
| 7220 | End Credits | 1 | flat | 1 | 1000 | 1000
| 7230 | Lower thirds & Locators (AE will do in-house) |  | allow | 1 | 0 | 0
| 7240 | Motion Graphics | 0 | hours | 1 | 250 | 0
| 7250 | Motion Control/Photo Animation | 0 | hours | 1 | 250 | 0
| 7290 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 7300 | VISUAL EFFECTS (VFX) |  |  |  |  | 2000
| 7310 | Archival footage restoration | 4 | hours | 1 | 250 | 1000
| 7320 | VFX-Boom removal, blurs, anonymization etc. | 4 | hours | 1 | 250 | 1000
| 7400 | ONLINE EDIT & COLOR CORRECTION |  |  |  |  | 11150
| 7410 | Digital 4K Online/Conform | 4 | days | 1 | 1000 | 4000
| 7420 | Color Grading | 5 | days | 1 | 1400 | 7000
| 7430 | Trim pass (e.g. HDR to SDR) |  | hours | 1 | 250 | 0
| 7490 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 7500 | POST SOUND |  |  |  |  | 31400
| 7510 | Sound design, edit, mix, layback (combined pkg 6-8 weeks edit, 10 day final mix) | 1 | flat | 1 | 30000 | 30000
| 7520 | Voiceover/ADR/Loop Group Recording | 5 | hours | 1 | 250 | 1250
| 7530 | Versioning/Additional Deliverables |  | allow | 1 | 5000 | 0
| 7580 | Dolby License |  | allow | 1 | 0 | 0
| 7590 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 7600 | OUTPUT & DELIVERABLES |  |  |  |  | 8900
| 7610 | Servicing elements QT burn-in for subs, sound, checks | 1 | allow | 1 | 500 | 500
| 7620 | ProRes 422 HQ 4K texted color corrected master | 1 | allow | 1 | 400 | 400
| 7621 | ProRes 422 HQ 4K textless color corrected master | 1 | allow | 1 | 400 | 400
| 7630 | IMF 4K Texted Streaming Master - incl. creation/QC/delivery | 1 | allow | 1 | 1500 | 1500
| 7640 | IMF 4K Textless Streaming Master - incl. creation/QC/delivery | 1 | allow | 1 | 1500 | 1500
| 7641 | IMF 4K Supplemental ("Fixes") Streaming Master - incl. creation/QC/delivery | 1 | allow | 1 | 750 | 750
| 7650 | DCP Theatrical Master - Color Correction P3 | 1 | allow | 1 | 800 | 800
| 7660 | DCP Theatrical Master (w/Open Captions for Accessibility) | 1 | DCP | 1 | 2000 | 2000
| 7670 | DCP Copies (Festival, theatrical) | 2 | DCP | 1 | 200 | 400
| 7680 | International deliverables @ 25FPS and 29.97FPS |  | allow | 1 | 2000 | 0
| 7685 | BluRay & DVD authoring & copies |  | allow | 1 | 1000 | 0
| 7687 | Backup & Archiving of Post Projects | 1 | allow | 1 | 500 | 500
| 7690 | Miscellaneous Deliverables | 1 | allow | 1 | 150 | 150
| 7700 | ARCHIVAL FOOTAGE & STILLS |  |  |  |  | 11450
| 7710 | Research & Preview fees | 1 | allow | 1 | 2000 | 2000
| 7720 | Footage licenses (Rights: All Media, Worldwide, in Perpetuity incl. Theatrical and Promotional Use) | 180 | seconds | 1 | 45 | 8100
| 7730 | Stills licenses (Rights: All Media, Worldwide, in Perpetuity incl. Theatrical and Promotional Use) | 4 | stills | 1 | 200 | 800
| 7740 | Footage transfer costs | 1 | allow | 1 | 400 | 400
| 7750 | Stills scanning/transfer costs |  | allow | 1 | 400 | 0
| 7760 | Shipping |  | allow | 1 | 200 | 0
| 7790 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 7800 | MUSIC/COMPOSER |  |  |  |  | 30150
| 7810 | Composer (all-in package includes musicians, score, and recording session) | 1 | flat | 1 | 30000 | 30000
| 7820 | Music Supervision (for licensing songs) |  | songs | 1 | 500 | 0
| 7830 | Music rights for licensed songs - Sync rights |  | songs | 1 | 3000 | 0
| 7840 | Music rights for licensed songs - Master rights |  | songs | 1 | 3000 | 0
| 7850 | Temp music purchases |  | allow | 1 | 250 | 0
| 7898 | Union and Guild Fees |  | % | 1 | 0 | 0
| 7890 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 7900 | SUBTITLES, CLOSED CAPTIONS, ACCESSIBILITY, ADD'L REQUIRED ITEMS |  |  |  |  | 7465
| 7910 | Translation & Subtitling (often for English master for multilingual projects) | 95 | minute | 1 | 12 | 1140
| 7912 | QC of Subtitles | 95 | minute | 1 | 5 | 475
| 7920 | Closed Captioning (CC) (can also be used as open captions) | 95 | minute | 1 | 15 | 1425
| 7930 | Audio Description Services (spoken audible descriptions of all visual-only elements of the film) | 95 | minute | 1 | 45 | 4275
| 7940 | On-screen ASL interpreter |  | allow | 1 | 6000 | 0
| 7950 | Final Transcript (including all audible and visual elements) (Locked Picture) (PA1 in-house) |  | cuts | 1 | 350 | 0
| 7960 | Combined Continuity and Spotting List (CCSL) |  | allow | 1 | 3350 | 0
| 7990 | Miscellaneous additional required items | 1 | allow | 1 | 150 | 150
|  | TOTAL |  |  |  |  | 142315.4885
|  | INSURANCE | # | UNIT | X | RATE | TOTAL $ COST
| 8000 | INSURANCE |  |  |  |  | 19350
| 8010 | Producer's Package (incl. Negative/Videotape & Faulty Stock/Camera/Processing; Extra Expense; Third Party Property Damage, Miscellaneous Equipment) | 1 | year | 1 | 6000 | 6000
| 8020 | General Liability | 2 | year | 1 | 2500 | 5000
| 8030 | Hired and Non-owned Auto Liability | 2 | year | 1 | 500 | 1000
| 8040 | Umbrella/Excess Liability |  | year | 1 | 1200 | 0
| 8050 | Worker's Compensation (partly covered thru payroll service) | 2 | year | 1 | 1000 | 2000
| 8060 | Additional or Owned Equipment Coverage |  | year | 1 | 1250 | 0
| 8070 | Special Coverages (e.g. Cast coverage, Kidnap, Ransom and Extortion coverage etc.) |  | year | 1 |  | 0
| 8080 | Errors & Omissions Insurance | 1 | flat | 1 | 4200 | 4200
| 8085 | Loss, Damage & Repair | 1 | allow | 1 | 1000 | 1000
| 8090 | Miscellaneous Additional Insurance Premiums | 1 | allow | 1 | 150 | 150
| 8100 | COVID-19 |  |  |  |  | 0
| 8110 | COVID Coordinator |  | days | 1 |  | 0
| 8120 | PPE (N95 Masks etc.) |  | allow | 1 |  | 0
| 8130 | Cleansing Supplies (Hand Santizer, Disinfecting Wipes, etc.) |  | allow | 1 |  | 0
| 8140 | Rapid self-tests |  | allow | 1 |  | 0
| 8150 | PCR Lab Tests |  | allow | 1 |  | 0
| 8190 | Miscellaneous |  | allow | 1 |  | 0
|  | TOTAL |  |  |  |  | 19350
|  | OFFICE & ADMINISTRATION | # | UNIT | X | RATE | TOTAL $ COST
| 9000 | OFFICE/ADMIN |  |  |  |  | 66115.1732 | 5.14%
| 9010 | Office Equipment (incl. computers, printers, scanners, networking, etc.) | 24.0185 | months | 1 | 180 | 4323.3256
| 9015 | Office Furnishings |  | allow | 1 | 2500 | 0
| 9020 | Office Software & Cloud Services (GSuite, MS Teams, etc.) 7ppl | 24.0185 | months | 7 | 14 | 2353.8106
| 9030 | Office Supplies | 24.0185 | months | 1 | 45 | 1080.8314
| 9040 | Photocopy & Fax | 24.0185 | months | 1 | 12 | 288.2217
| 9050 | Postage/Messenger/Courier | 24.0185 | months | 1 | 90 | 2161.6628
| 9060 | Office Meals & Craft Service (Working Meals/Deadlines) | 24.0185 | months | 1 | 180 | 4323.3256
| 9070 | Production Office - Rent (Fully accessible office incl. parking, offices, bathrooms, etc. See 9080.) | 24.0185 | months | 1 | 1500 | 36027.7136
| 9071 | Production Office - Parking Spaces (x3) | 24.0185 | months | 3 | 25 | 1801.3857
| 9072 | Production Office - Electric/Water/Gas/Alarm | 24.0185 | months | 1 | 200 | 4803.6951
| 9073 | Production Office - Telephone/High Speed Internet | 24.0185 | months | 1 | 65 | 1561.2009
| 9074 | Production Office - Cleaning Service | 24.0185 | months | 1 | 259.8 | 6240
| 9080 | Accessibility for production office (Accessibility requirements will vary and could include a fully wheelchair-accessible production office, modified desks and/or chairs, screenreaders, accessible toilets, additional lighting, floor markings, rest space, quiet space, interpreter rest space, service animal rest space, etc.) | 1 | allow | 1 | 1000 | 1000
| 9090 | Miscellaneous | 1 | allow | 1 | 150 | 150
| 9100 | PROFESSIONAL SERVICES |  |  |  |  | 35806.455
| 9110 | Production Legal & Clearance Counsel | 1 | allow | 1 | 15000 | 15000 | 1.166%
| 9120 | Fact-Checking | 50 | hours | 1 | 50 | 2500
| 9130 | Title Report | 1 | flat | 1 | 400 | 400
| 9140 | Accounting & Bookkeeping Services | 24.0185 | months | 1 | 600 | 14411.0855
| 9141 | LLC/Corp Entity Formation | 1 | allow | 1 | 500 | 500
| 9142 | LLC/Corp Tax Prep | 2 | years | 1 | 1200 | 2400
| 9143 | LLC/Corp Taxes | 2 | years | 1 | 25 | 50
| 9150 | Copyright Registration | 1 | allow | 1 | 65 | 65
| 9160 | MPAA Rating |  | allow | 1 | 5000 | 0
| 9170 | International Currency Exchange Gain/Loss |  | allow | 1 | 0 | 0
| 9175 | Bank Fees | 24.0185 | months | 1 | 20 | 480.3695
|  | TOTAL |  |  |  |  | 101921.6282
| BTL | SUBTOTAL BELOW-THE-LINE (BTL) |  |  |  |  | 879900.6866
|  | PUBLICITY, PROMOTION, WEBSITE, FESTIVALS, IMPACT, DISTRIBUTION (Excluded from production budget by some funders) | # | UNIT | X | RATE | TOTAL $ COST
| 10000 | PROMOTIONAL MATERIALS |  |  |  |  | 17290
| 10010 | Poster/Key Art Design | 1 | flat | 1 | 4000 | 4000
| 10020 | Poster reproduction (offset printing) | 100 | pieces | 1 | 1.5 | 150
| 10030 | Postcards (4.25" x 6", 4-color both sides) | 3000 | pieces | 1 | 0.04 | 120
| 10040 | PDF Electronic Press Kits |  | allow | 1 | 565 | 0
| 10050 | Trailer & Promo Clips - Editing | 2 | weeks | 1 | 3000 | 6000
| 10060 | Trailer & Promo Clips - Finishing, Mix & Delivery | 1 | allow | 1 | 2000 | 2000
| 10070 | Website Design & 1yr domain/hosting/maintenance | 1 | allow | 1 | 4000 | 4000
| 10080 | Trailer & Promo Clips - Subtitling, Closed Captions, Accessibility
|  | Translation & Subtitling (often for English master for multilingual projects) | 10 | minute | 1 | 12 | 120
|  | Closed Captioning (CC) or Open Captioning (OC) | 10 | minute | 1 | 15 | 150
|  | Audio Description Services (spoken audible descriptions of all visual-only elements of the film) | 10 | minute | 1 | 45 | 450
|  | On-screen ASL interpreter |  | allow | 1 | 800 | 0
|  | Transcript (including all audible and visual elements) | 1 | allow | 1 | 300 | 300
| 10090 | Misc Promotional Materials |  | allow | 1 | 150 | 0
| 10100 | PROMOTION & PUBLICITY SERVICES |  |  |  |  | 10000
| 10110 | Publicist | 1 | allow | 1 | 10000 | 10000
| 10120 | Social Media Promotion/Community Management |  | months | 1 | 2000 | 0
| 10130 | Accessibility Coordinator/ Production Access Coordinator |  | days | 1 | 450 | 0
| 10190 | Misc Promotion & Publicity Services |  | allow | 1 | 150 | 0
| 11000 | FILM FESTIVALS |  |  |  |  | 740
| 11010 | Application Fees | 10 | festivals | 1 | 50 | 500
| 11020 | DCP Shipping | 3 | festivals | 1 | 80 | 240
| 12000 | IMPACT, OUTREACH AND EDUCATION |  |  |  |  | 7500
This section mentions a few line items that could help with assessing impact, outreach and education. An extensive impact campaign requires its own separate budget. For excellent impact resources, including sample budgets, visit Doc Society's ImpactGuide.org
| 12010 | Impact Agency Consultant Fee to assess impact potential/strategy | 1 | allow | 1 | 2500 | 2500
| 12020 | Braintrust & Consultant Fees to assess impact potential/strategy | 1 | allow | 1 | 4000 | 4000
| 12030 | Impact Proposal & Budget | 1 | allow | 1 | 1000 | 1000
| 12080 | Accessibility for Impact, Outreach and Education |  | allow | 1 |  | 0
| 13000 | HYBRID DISTRIBUTION |  |  |  |  | 2000
| 13010 | Distribution Consultation to evaluate hybrid distribution | 1 | allow | 1 | 2000 | 2000
| 13020 | Hybrid Distribution Proposal & Budget |  | allow | 1 | 1000 | 0
| 14000 | FESTIVALS, IMPACT, DISTRIBUTION TRAVEL |  |  |  |  | 3170
| 14010 | Airfare/Railfare | 3 | R/T | 1 | 400 | 1200
| 14020 | Add'l baggage fees for equipment | 0 | fees | 1 | 75 | 0
| 14030 | Hotel/Lodging | 3 | hotel nights | 2 | 200 | 1200
| 14040 | Local Transport/Taxis/Car Service/Car Rental/Public Transport | 1 | allow | 1 | 200 | 200
| 14050 | Meals & Per Diem | 3 | days | 2 | 70 | 420
| 14080 | Accessibility for Travel (see 1280 for details) |  | allow | 1 | 500 | 0
| 14090 | Misc Festival Travel | 1 | allow | 1 | 150 | 150
| 15000 | AWARDS CAMPAIGN (Excluded from production budget by some funders) |  |  |  |  | 0
| 15010 | Publicist |  | allow | 1 |  | 0
| 15020 | Screenings |  | allow | 1 |  | 0
| 15021 | Venue Rentals |  | allow | 1 |  | 0
| 15022 | Catering |  | allow | 1 |  | 0
| 15030 | Advertising |  | allow | 1 |  | 0
| 15040 | Social Media |  | allow | 1 |  | 0
| 15050 | E-blasts |  | allow | 1 |  | 0
| 15060 | Campaign Costs |  | allow | 1 |  | 0
| 15090 | Misc Awards Campaign costs |  | allow | 1 | 150 | 0
| 15100 | AWARDS TRAVEL |  |  |  |  | 0
| 15110 | Airfare/Railfare |  | allow | 1 |  | 0
| 15120 | Add'l baggage fees for equipment |  | allow | 1 |  | 0
| 15130 | Hotel/Lodging |  | allow | 1 |  | 0
| 15140 | Local Transport/Taxis/Car Service/Car Rental/Public Transport |  | allow | 1 |  | 0
| 15150 | Meals & Per Diem |  | allow | 1 |  | 0
| 15180 | Accessibility for Travel (see 1280 for details) |  | allow | 1 |  | 0
| 15190 | Misc Awards Travel |  | allow | 1 | 150 | 0
|  | TOTAL |  |  |  |  | 40700
|  | SUBTOTAL PUBLICITY, PROMOTION, WEBSITE, FESTIVALS, IMPACT, DISTRIBUTION |  |  |  |  | 40700
|  | SUBTOTAL ABOVE-THE-LINE (ATL) |  |  |  |  | 255615.15
|  | SUBTOTAL BELOW-THE-LINE (BTL) |  |  |  |  | 879900.6866
|  | SUBTOTAL PUBLICITY, PROMOTION, WEBSITE, FESTIVALS, IMPACT, DISTRIBUTION |  |  |  |  | 40700
|  | COMBINED SUBTOTAL |  |  |  |  | 1176215.837
|  | CONTINGENCY | 7.5% |  |  | 1176215.837 | 88216.1878
|  | FISCAL SPONSOR FEES (applied to USA grant funds only) | 5% |  |  | 435000 | 21750
|  | PRODUCTION SERVICES FEE (approx 10%, generally for commissioned projects) |  |  |  |  | 0
|  | GRAND TOTAL |  |  |  |  | 1286182.024

## 5. Budget Topsheet
0
UNTITLED EXCELLENT DOCUMENTARY FILM
BUDGET DATE: 3/1/2024
| 0 |  |  | 0 | 0 | 0
| PRODUCTION COMPANY: Great Docu Films Inc. |  | 0 | Research: | 18 | weeks
| DIRECTOR : Excellent Director |  |  | Prep: | 9 | weeks (overlaps with research)
| PRODUCER: Excellent Producer |  |  | Shoot Days: | 12 interview days+53 vérité days
| EDITOR: Super Cutter |  |  | Shoot/Production Period: | 52 | weeks
| LINE PRODUCER: OnBudget Smithee |  |  | Edit: | 40 | weeks (overlaps with shoot)
| 0 |  |  | Finishing/Post: | 16 | weeks
| BUDGET PREPARED BY: OnBudget Smithee |  |  | TOTAL WEEKS: | 104 | weeks
| 0 |  |  | TOTAL MONTHS: | 24.0185 | months
| LENGTH: 95 min (approx.) |  |  | DELIVERY DATE: | TBD | 0
| Original Footage: 90 min |  |  | 0 | 0 | 0
| Archival Footage: 3 min |  |  | LOCATIONS: | New York, Los Angeles, Houston
| Graphics/Animation: 2 min (Opening title, End credits) |  |  | UNION/GUILD: | Non-Union
| 0 |  |  | 0 | 0
| SHOOTING FORMAT: 4K UHD |  |  | ADDITIONAL NOTE #1: | 0
| EDITING FORMAT: Avid DNX36 offline |  |  | ADDITIONAL NOTE #2: | 0
| FINISHING FORMAT: 4K UHD (Quicktime, IMF, DCP) |  |  | ADDITIONAL NOTE #3: | 0
0
| ACCT | DESCRIPTION |  |  |  | AMOUNT
| 1000 | STORY RIGHTS, RESEARCH & PROJECT DEVELOPMENT |  |  |  | 10615.15
| 2000 | PRODUCING STAFF |  |  |  | 245000
| 3000 | TALENT |  |  |  | 0
|  | SUBTOTAL ABOVE-THE-LINE (ATL) |  |  |  | 255615.15
| 4000 | PRODUCTION STAFF |  |  |  | 180536.72
| 4100 | PRODUCTION CREW |  |  |  | 87332.15
| 4200 | EDITORIAL STAFF |  |  |  | 271108.7
| 4300 | CONSULTANTS |  |  |  | 0
| 5000 | CAMERA |  |  |  | 26402
| 5100 | SOUND |  |  |  | 6271
| 5200 | LIGHTING & GRIP |  |  |  | 6505
| 5300 | STUDIO FACILITIES |  |  |  | 0
| 5400 | SET DRESSING |  |  |  | 0
| 5500 | WARDROBE |  |  |  | 0
| 5600 | MAKEUP & HAIR |  |  |  | 1000
| 5700 | PRODUCTION FILM & LAB |  |  |  | 8950
| 5800 | LOCATION EXPENSES |  |  |  | 9143
| 5900 | LOCATION TRANSPORTATION |  |  |  | 11505
| 6000 | PRODUCTION TRAVEL |  |  |  | 7560
|  | PRODUCTION TOTAL |  |  |  | 616313.57
| 7000 | EDITORIAL EQUIPMENT, FACILITY & SUPPLIES |  |  |  | 33850.4884
| 7100 | FORMAT CONVERSIONS |  |  |  | 800
| 7200 | GRAPHICS, TITLES & EFFECTS |  |  |  | 5150
| 7300 | VISUAL EFFECTS (VFX) |  |  |  | 2000
| 7400 | ONLINE EDIT & COLOR CORRECTION |  |  |  | 11150
| 7500 | POST SOUND |  |  |  | 31400
| 7600 | OUTPUT & DELIVERABLES |  |  |  | 8900
| 7700 | ARCHIVAL FOOTAGE & STILLS |  |  |  | 11450
| 7800 | MUSIC/COMPOSER |  |  |  | 30150
| 7900 | SUBTITLES, CLOSED CAPTIONS, ACCESSIBILITY, ADD'L REQUIRED ITEMS |  |  |  | 7465
|  | POST-PRODUCTION TOTAL |  |  |  | 142315.4885
| 8000 | INSURANCE |  |  |  | 19350
| 8100 | COVID-19 |  |  |  | 0
| 9000 | OFFICE/ADMIN |  |  |  | 66115.1732
| 9100 | PROFESSIONAL SERVICES |  |  |  | 35806.455
|  | ADMIN/OTHER TOTAL |  |  |  | 121271.6282
|  | SUBTOTAL BELOW-THE-LINE (BTL) |  |  |  | 879900.6866
| 10000 | PUBLICITY, PROMOTION, WEB, FESTIVALS, IMPACT, DISTRIBUTION |  |  |  | 40700
|  | SUBTOTAL PUBLICITY, PROMO, WEB, FESTS, IMPACT, DISTRIB |  |  |  | 40700
|  | SUBTOTAL |  |  |  | 1176215.837
|  | CONTINGENCY |  | 7.5% |  | 88216.1877
|  | FISCAL SPONSOR FEE (applied to USA grants only) |  | 5% |  | 21750
|  | PRODUCTION SERVICES FEE (approx 10%, if applicable) |  |  |  | 0
|  | GRAND TOTAL |  |  |  | 1286182.024

## 6. Finance Plan
0
UNTITLED EXCELLENT DOCUMENTARY FILM
FINANCE PLAN DATE: 3/1/2024
PRODUCTION COMPANY: Great Docu Films Inc.
DIRECTOR : Excellent Director
PRODUCER: Excellent Producer
FINANCE PLAN
| FUNDS SECURED | AMOUNT | % | RIGHTS GRANTED | REVENUE PARTICIPATION | << You definitely need the "Revenue Participation" in your internal finance plan, but might or might not decide to share this information externally.
| Grant 1 | 75000 | 5.831% | none | none
| Grant 2 | 150000 | 11.66% | none | none
| Grant 3 | 100000 | 7.775% | none | none
| Country 1 Broadcaster | 250000 | 19.44% | USA Public TV | net profit
| Country 2 Broadcaster | 50000 | 3.887% | UK Public TV | none
| Private Investor 1 | 50000 | 3.887% | none | recoup+10% premium+net profit
| Private Investor 2 | 50000 | 3.887% | none | recoup+net profit
| Crowdfunding | 50000 | 3.887% | none | none
| Producer Cash (Advance) | 25000 | 1.944% | none | recoup
| TOTAL FUNDS SECURED | 800000 | 62.2%
| FUNDS PENDING / STILL TO BE RAISED | AMOUNT | % | STATUS | EXPECTED NOTIFICATION DATE
| Grant 1 | 40000 | 3.11% | Applied 31May2024 | 2024-09-01
| Grant 2 | 40000 | 3.11% | Applied 15June2024 | 2024-10-15
| Grant 3 | 30000 | 2.332% | Will apply | none
| Country 3 Broadcaster | 50000 | 3.887% | In Discussions | Fall 2024
| Country 4 Broadcaster | 38000 | 2.954% | In Discussions | Fall 2024
| TBD/Additional funding to be sought | 288182.0244 | 22.41% | none | none
| TOTAL FUNDS PENDING | 486182.0244 | 37.8%
| FUNDS SECURED+PENDING | 1286182.024 | 100%
| TOTAL BUDGET | 1286182.024 | 100%